# SmartShield — Sprint 0 Dependency Chart

## 1. High-level dependency structure

┌──────────────────────┐

│  PROJECT SCOPE / MVP │

│  Vulnerability Scope │

└──────────┬───────────┘

│

┌───────────────┼────────────────┐

│               │                │

▼               ▼                ▼

IR Requirements   Graph Requirements   Detector

│               │              Requirements

│               │                │

▼               ▼                ▼

┌───────┐      ┌──────────┐    ┌──────────────┐

│ IR v1 │◄────►│CFG/CG v1 │◄──►│Detector Spec │

└───┬───┘      └────┬─────┘    └──────┬───────┘

│               │                  │

└───────────────┼──────────────────┘

│

▼

┌─────────────────────┐

│ Cross-module        │

│ Interface Contract  │

└──────────┬──────────┘

│

┌───────────────┼────────────────┐

▼               ▼                ▼

Test Cases      Dataset Plan     Performance

/ Evaluation     / ML Plan         Plan

│               │                │

└───────────────┼────────────────┘

▼

┌─────────────────────┐

│ Sprint 1 Build Plan │

└─────────────────────┘

# 2. Actual member-to-member dependency graph

This is the chart I would give the team.

┌───────────────┐

│ TEAM DECISION │

│ MVP + Scope   │

└───────┬───────┘

│

▼

┌────────────────────────┐

│ PATHAK — PA-01         │

│ Vulnerability Research │

└───────────┬────────────┘

│

┌─────────────┴─────────────┐

▼                           ▼

┌──────────────────┐        ┌──────────────────┐

│ YOU — U-01       │        │ AAYUSH — AY-01   │

│ IR Requirements  │        │ Detector Spec    │

└────────┬─────────┘        └────────┬─────────┘

│                           │

│              ┌────────────┘

│              │

▼              ▼

┌────────────────────────────┐

│ PARIT — P-01 / P-02       │

│ CFG + Call Graph           │

└────────────┬───────────────┘

│

▼

┌────────────────────────────┐

│ YOU — U-02                 │

│ Cross-module Interfaces    │

└────────────┬───────────────┘

│

┌────────┴────────┐

▼                 ▼

┌─────────────────┐  ┌──────────────────┐

│ AAYUSH — AY-02  │  │ PATHAK — PA-02   │

│ DetectionResult │  │ Dataset Analysis │

└────────┬────────┘  └────────┬─────────┘

│                    │

└──────────┬─────────┘

▼

┌──────────────────┐

│ PATHAK — PA-03  │

│ ML Baseline     │

└────────┬─────────┘

│

▼

┌─────────────────────┐

│ SPRINT 1 READINESS │

└─────────────────────┘

There are also two largely independent streams:

YOU

│

▼

Performance Requirements

│

▼

Performance Plan

AAYUSH

│

▼

Test Contract Corpus

│

▼

Evaluation Foundation

They eventually connect to the main system but should not block the core architecture decisions.

# 4. Recommended execution order

I would tell the team to work in this sequence.

## Step 1 — Everyone

### Agree on:

- What SmartShield's MVP actually means

- Initial vulnerability candidates

- What is explicitly outside scope

Output: MVP_SCOPE.md

This is the only genuinely team-wide prerequisite.

## Step 2 — Pathak

### PA-01: Vulnerability research

Pathak investigates the candidate vulnerabilities and produces evidence for:

Candidate

↓

Importance

↓

Static-analysis suitability

↓

Dataset availability

↓

Difficulty

↓

MVP recommendation

This informs everyone else.

# Step 3 — Shermale + Aayush

These should happen in parallel.

### You

Define:

"What information should our internal representation contain?"

### Aayush

Define:

"What information would a vulnerability detector need?"

They should then compare.

IR proposal

│

▼

┌─────────────────┐

│ Information gap │

└─────────────────┘

▲

│

Detector needs

This is important because otherwise you may design a beautiful IR that lacks information required for actual vulnerability detection.

# Step 4 — Parit

Once the IR is reasonably stable:

Parit determines:

"Given this representation, how do we construct the CFG and Call Graph?"

His work should feed back into your IR.

So this is not:

You → finished IR → Parit

It is:

You ───────► IR draft ───────► Parit

▲                              │

│                              │

└──── missing information ◄────┘

That's the correct Agile interaction.

# Step 5 — Cross-module interface

Once those three areas have interacted:

IR

+

CFG

+

Call Graph

+

Detector requirements

↓

Cross-module contracts

This is when U-02 becomes meaningful.

# Step 6 — Parallel supporting work

After the architecture starts stabilizing:

### Pathak

Dataset → ML feasibility.

### Aayush

Detector specifications → test contracts.

### Shermale

Performance requirements → measurement plan.

These should prepare Sprint 1 rather than attempt to implement Sprint 1 prematurely.

# 5. What must be finished before Sprint 1?

This is our Sprint 0 exit dependency graph:

MVP SCOPE

│

▼

VULNERABILITY SHORTLIST

│

┌───────────┼────────────┐

▼           ▼            ▼

IR          CFG/CG     DETECTOR

v1           v1          v1

│           │            │

└───────────┼────────────┘

▼

INTERFACES v1

│

┌───────────┼─────────────┐

▼           ▼             ▼

TEST CORPUS   DATASET       BENCHMARK

│           │             │

└───────────┼─────────────┘

▼

SPRINT 1 PLAN

If one of these isn't perfect, that's okay.

The important word is v1.

We want:

sufficiently stable to build against

not:

theoretically perfect forever.

# 6. Things that should NOT become dependencies

This is equally important.

Do not allow:

ML → IR

to block the core system.

ML is an extension of the baseline analysis.

Similarly:

Frontend → Core analysis

should not block analysis development.

And:

Remediation → Detector

is a dependency, but:

Remediation → MVP

should not become a blocker.

The architecture should allow:

Core Engine

│

┌────────────┼────────────┐

▼            ▼            ▼

Rule-based       ML        Remediation

Analysis      Analysis     Extension

rather than making everything mandatory for the core pipeline.

# 7. The most important instructions

"Your task is not to finish your entire module during Sprint 0. Your task is to remove uncertainty about your module so that implementation can begin cleanly in Sprint 1."

"If you discover that another module must change for your work to be possible, raise that dependency immediately. Do not silently work around it or independently redesign the other module."

## Sprint 0 final dependency chain

The shortest version you can keep beside the project board is:

MVP

↓

Vulnerability Scope

↓

┌─────────────┬──────────────┬──────────────┐

│             │              │

IR           CFG/CG       Detector Spec

│             │              │

└─────────────┴──────────────┘

↓

Interface Contracts

↓

┌────────┼─────────┐

│        │         │

Tests    Dataset   Benchmark

│        │         │

└────────┼─────────┘

↓

Sprint 1 Ready